## New
WAYLEAVE MANAGEMENT SYSTEM
CUTOMISATION 24/04/2023
TASK | DETAILS | Front End(Y/N) | Backend(Y/N) | Database(Y/N) | Start Date | End Date | SENIOR(HRS) | TOTAL | JUNIOR(HRS) | TOTAL2
New Wayleave/ Renewal/Resubmission | Re-submissions: System to allow only 3 resubmissions Disclaimer message to be added when resubmission option is chosen: only 3 re-submissions allowed. (re-submission 1 of 3) | Y | Y | Y | 2023-05-03 | 2023-05-15 | 70 | 80500 | 15 | 11625
Future automation-system to determine project size | Logic to determine size of project by prompting the applicant with guiding information and questions | Y | Y | Y | 2023-05-16 | 2023-05-25 | 60 | 69000 | 30 | 23250
Type of excavation Drop down list | Excavation type dropdown: Directional Drilling, Open Excavation, Pipe jacking, Other (list) | Y | Y | N | 2023-05-26 | 2023-05-29 | 20 | 23000 | 15 | 11625
Draw polygon | Geo reference applications to be routed to the relevant regions/ districts depending on the location of the polygon | Y | Y | N | 2023-05-30 | 2023-06-21 | 180 | 207000 | 40 | 31000
Upload Mandatory list documentation | A mandatory list of documents will be required as an upload before the applicant can proceed to the next step based on the project size selected. System must guide Applicant as to what document to attach where. System to name document. | Y | Y | Y | 2023-05-31 | 2023-06-06 | 30 | 34500 | 10 | 7750
Select Standard conditions per department | Consolidate standard conditions per department as a dropdown option and re-purpose the existing drop down list for commonly used special conditions. Reviewer to select and edit these but also have a free text field available. | Y | Y | Y | 2023-06-07 | 2023-06-13 | 40 | 46000 | 20 | 15500
Draw Polygon/ Upload Documents (Mandatory coordinates (latitude and longitude)) | Applicant should be able to hover over the map to view coordinates | Y | Y | Y | 2023-06-14 | 2023-06-23 | 60 | 69000 | 30 | 23250
Start Applicant selects to apply for a PTW after a wayleave is approved | When a wayleave is approved an option to apply for PTW should be activated. Once selected, details of affected departments for kick-off to be displayed in a new window. | Y | Y | Y | 2023-06-26 | 2023-06-27 | 15 | 17250 | 30 | 23250
Suspension of PTW | Select suspension and provide reasons and remedial measures. In the event of violation that requires suspension of Permit, LD to select Suspension and provide reasons as well as requirements for reinstatement | Y | Y | Y | 2023-06-28 | 2023-07-03 | 30 | 34500 | 15 | 11625
Permit to Work sign-off | System to allow electronic signature | Y | Y | Y | 2023-07-04 | 2023-07-13 | 60 | 69000 | 30 | 23250
Permit to work-consolidation | System to detect and indicate which departments approved the PTW | Y | Y | Y | 2023-07-13 | 2023-07-15 | 20 | 23000 | 15 | 11625
Infringement | Infringement tab. LD provide notice of infringement and contact details for further information. Applicant to have the option to mark infringement rectified | Y | Y | Y | 2023-07-19 | 2023-07-28 | 60 | 69000 | 20 | 15500
Completion Certificates | Generate completion certificate. LD to issue a completion certificate once As-built information is available and all infringement payments settled. | Y | Y | Y | 2023-07-31 | 2023-08-11 | 70 | 80500 | 30 | 23250
Refund Processed and Notification to Applicant | LD to select ‘Refund Processed’ in the WLMS. If this has not been selected, the System will not recognise the application as complete. Electronic notification is sent to the Applicant, confirming that the application has been concluded. | Y | Y | Y | 2023-08-14 | 2023-08-21 | 50 | 57500 | 30 | 23250
Construction Monitoring | Comments to be uploaded during site inspections with date stamp | Y | Y | Y | Completed | Completed | 0 | 0 | 0 | 0
Upload as-built information | Applicant to upload as-built plans | Y | Y | Y | Completed | Completed | 0 | 0 | 0 | 0
Re-design invoicing for split journals and configurations | Admin fee will only be applicable to applications affecting Urban Mobility,Water and future departments. | Y | Y | Y | 2023-08-22 | 2023-08-29 | 60 | 69000 | 30 | 23250
The facilitation process if a specific line department rejection | Sending the application back to initial stage to edit application e.g. Redrawing polygon. If a department rejects, then move the application in accordance with the stage flow thereafter. | Y | Y | Y | 2023-08-30 | 2023-09-13 | 90 | 103500 | 20 | 15500
Clients proposing start and end dates | Adding functionality for the client to input start date and end date at the end of the approval process | Y | Y | Y | 2023-09-14 | 2023-09-18 | 20 | 23000 | 10 | 7750
Request for kick-off meetings | Adding fuctionalilty to scheduling meeting, request, track and alerting all relevent users | Y | Y | Y | 2023-09-19 | 2023-10-03 | 80 | 92000 | 20 | 15500
Recording of deposits | Adding fuctionalilty to record existing guarantees per client with diminishing balance | Y | Y | Y | 2023-10-04 | 2023-10-13 | 60 | 69000 | 20 | 15500
Testing debugging(QA) | Testing and making sure all new additions to the system is in working order and does not affect the functionality of pre-existing components. Testing code after adding new features to a system is crucial for ensuring the quality, reliability and stability of the system. Creating a well-designed testing process helps us identify potential issues and bugs before the system is deployed to production, reducing the risk of downtime or data loss. We will draw up a testing plan for developers to use which will determine the scope of the testing effort, identify the target audience, users and user roles, and develop a testing strategy that meets the assosiated to all users of the WLMS system. Develop test cases that cover the new features and changes in the system. These test cases are comprehensive and cover a range of scenarios. Run the test cases on the system to check for any issues or bugs. Review the test results and determine if the new features and changes in the system have any unintended consequences or impact on other parts of the system. Document the results of the testing process and provide a clear and concise report. Address any issues or bugs identified during the testing process by making the necessary code changes and retesting the system. In conclusion, testing code after adding new features is a critical part of software development and helps to ensure that the system is functioning as intended and delivering the desired user experience. The testing process is essential for reducing the risk of system failures and improving the overall quality of the system. |  |  |  | 2023-10-16 | 2023-11-06 | 130 | 149500 | 60 | 46500
TOTALS | [6 empty] | 310 | 356500 | 100 | 77500
TOTAL FOR BOTH DEVELOPERS (1695 HOURS) | [9 empty] | 434000
PROJECT MANAGEMENT FEE (200 HOURS) | [9 empty] | 230000
TOTAL | [9 empty] | 664000
VAT | [9 empty] | 99600
GRAND TOTAL | [9 empty] | 763600
HOURLY RATES
POSITION | RATE
SENIOR DEVELOPER | 1150
JUNIOR DEVELOPER | 775
PROJECT MANAGER | 1150

## Completed
WAYLEAVE MANAGEMENT SYSTEM
CUTOMISATION 24/04/2023
TASK | DETAILS | Front End(Y/N) | Backend(Y/N) | Database(Y/N) | SENIOR(HRS) | TOTAL | JUNIOR(HRS) | TOTAL2
Redesign Process Flows | Added manager approval and functionality to send back to LD reviewer for further assessment. Changed hopper functionality from user selecting application to manager assigning to user | Y | Y | Y | 50 | 57500 | 20 | 15500
WBS Functionality | Added additional function for request for WBS number. This button will turn on and off based on whether user is internal or external | Y | Y | Y | 30 | 34500 | 20 | 15500
TOTALS |  |  |  |  | 80 | 92000 | 40 | 31000
TOTAL FOR BOTH DEVELOPERS (120 HOURS) | [7 empty] | 123000
VAT | [7 empty] | 18450
GRAND TOTAL | [7 empty] | 141450
HOURLY RATES
POSITION | RATE
SENIOR DEVELOPER | 1150
JUNIOR DEVELOPER | 775